## Slide 1
Risk Management Update
to GM CSD Board of Directors
Kim Seney - 12/11/2020
We are HERE!

## Slide 2: Prioritization Process Update & Methodology
All identified Risk statements were provided to all Board members via email for assessment and rating of “Likelihood” to occur and “Potential Impact” if it should occur
4 of 5 Board Members and GM provided ratings on these dimensions
Board member ratings were averaged to determine a whole number score for “Likelihood” and “Impact” for each statement
    Scores with .25 were rounded down (e.g. 2.25 was rated as 2)
    Scores with .75 were rounded up (e.g. 3.75 was rated as 4)
    Scores with .50 were tipped up or down based on adding GM score to average
Each item was then assigned to Ratings “Critical”, “High”, “Moderate” and “Low” based on previously approved Risk Ranking Criteria and Prioritization Matrix

## Slide 3: Summary of Prioritization Outcomes
Note: 3 New Risk statements were suggested during rating process – these will be sent to Board Members for rating; they will be added to the composite Risk Assessment
 |  | Level of Impact |  |  | 
 |  | 1 (Minor) | 2 (Moderate) | 3 (Major) | 4 (Critical)
Likelihood |  | Risk Ranking |  |  | 
4 | Almost Certain (> 80% likely) | 0 | 0 | 2 | 2
3 | Likely (40 - 80% likely) | 0 | 3 | 22 | 9
2 | Possible (10 - 40% likely) | 0 | 5 | 4 | 1
1 | Unlikely (< 10% likely) | 0 | 0 | 0 | 0
 | KEY: | CRITICAL | HIGH | MODERATE | LOW
 | # of Risk Items: | 13 | 23 | 12 | 0

## Slide 4: List of “Critical” Risks

## Slide 5: Fully Prioritized Risk Items – Page 1
Item # | Identified Risk | Rating
A-2 | Fire in the community (structure or wildland) severly damages infrastructure - contingency plan | Critical
A-3 | Fire in the community (structure or wildland) severly damages infrastructure - prevention plan | Critical
A-5 | Lack of documented District-wide incident response plan for compromised water and sewer services (including Monitoring, Response, Communication, Contacts - including Vendors, etc.) | Critical
A-12 | Risk to system during sustained power outages with documented response plan | Critical
D-3 | Lack of operational and administrative documentation will be gap with employee transitions | Critical
E-3 | Not aware of who is responsible for new laws and codes - trust somebody must do something though | Critical
F-1 | Water supply is comprised and not potable - for whatever reason - do we have backup for safe, clean water | Critical
F-2 | Quantity of water is diminished and not enough water to meet demand | Critical
G-1 | Need to expand capcity as community grows - are we capable? | Critical
G-3 | Lack of reliable (and visible) process for identifying sewer issue (quality or quantity) proactively causes someoneto be harmed | Critical
H-4 | Land continguous to community is not fully managing fire risk - define our role as influencers | Critical
H-6 | District does not have enough water to support effective fire suppression | Critical
H-7 | The district does not have enough water pressure to support fire response | Critical
A-1 | A fire in the community (structure or wildland) results in legal or other liability for CSD | High
A-6 | Lack of documented incident response plan for fire (structure or wildland) in or near community | High
A-7 | We are reactive and too many competing priorities for limited resources - need agreed upon strategic business plan to prioritize | High
A-9 | Need a set process to ensure consistency in all aspects of district business to ensure compliance with laws and policies, along with regular audits and result readouts to board. (Field audits, Admin audits, Personnel audits, etc) | High
A-10 | No current process for review, update, additional and archiving or Policies | High
A-11 | Need to instill a more proactive mindset in culture - very reactive - need more contingency planning | High
A-13 | Not as strong a culture of Safety as could be to ensure health and welfare of staff and volunteers | High
B-1 | Lack of understanding, modeling and planning around income/revenue exposure with single lot owner (100+ lots) demonstrating late/slow payment history, impacting >20% of recurrning income | High
B-2 | Lack of understanding, modeling and planning around income/revenue exposure with commercial properties, in addition to 100+ single lot ownership, with demonstrated payment issues | High
B-4 | Economic growth slower or faster than our infrastructure plan and ability to finance | High

## Slide 6: Fully Prioritized Risk Items – Page 2
Item # | Identified Risk | Rating
B-5 | No clear plan for what money is needed and when to maintain and expand district as needed | High
B-6 | Gap in funding sources to support needed investment for maintenance and expansion | High
C-1 | Exposure of customer data and privacy - need audit and improvement implementation plan with funding | High
C-2 | Asset Protection audit and plan to address issues identified, including training of personnel | High
C-6 | Our investment policy has not been updated recently and may not be in compliance with current laws and regulations | High
D-2 | Lack of documentation of processes, SOPs puts district in position of not being able to demonstrate we've done everything we are required to do | High
D-4 | Lack of external communication plan and delivery creates gaps in community and customer perceptions - need more, and need process for ensuring attention to detail and professionalism as well as understanding the audience and writing to them | High
E-1 | With regard to compliance, everyone seems to think someone else is doing it | High
E-4 | GM and staff should track (because they are more aware of how work is done and can assess impact) and bring impact assessment and recco to Board | High
F-3 | Lack of reliable (and visible) process for identifying water issue (quality or quantity) proactively causes someone to be harmed | High
G-2 | Leech fields becoming smelly if abundant rain/snow year | High
H-3 | Green waste continues to be difficult for owners to access, adding to fire risk and pressure on district to provide solutions | High
H-8 | Iron Horse fire station offers an opportunity that we should consider - it is an asset - if we don't develop plan, we risk losing opportunity | High
A-4 | CSD equipment or employee causes fire in the community (strucure or wildland) | Moderate
A-8 | Building growth creates demand beyond current capacity - need to update infrastructure plan | Moderate
B-3 | Without financial indicators (e.g. operating cash on hand, aging receivables summary, etc) tracked and published on regular schedule, may not be aware of financial issue as soon as possible and lose ability to react | Moderate
C-3 | Eroding customer confidence - can we support build out? | Moderate
C-4 | Customer/community confidence may erode as residents start seeing more water notices | Moderate
C-5 | Lack of transparency about district strategic plans, financial situation and ability to fund existing maintenance and future build out | Moderate
D-1 | Lack of documented training plan for each staff role (by job title) and Board members limits personnel effectiveness and engagement | Moderate
D-5 | Lack of commitment and funding for robust development process for staff and board will result in less than optimal organization | Moderate
E-2 | Aware of Financial Audit | Moderate
H-1 | Lack of work on fire issues by HOA puts undo burden on CSD - do we have enough resource allocated given this new situation | Moderate
H-2 | Current fire staff not on site and we need someone here | Moderate
H-5 | Terms of Fire Protection contract not being fulfilled or documented through audit | Moderate

## Slide 7: Task Timeline Update:
Steps | Target Date | Status
Plan & Establish Process |  | COMPLETE
Identify Risks |  | COMPLETE
High Level Assessment & Prioritization |  | COMPLETE
Deep Level Assessment |  | 
Recommend Top Risks for immediate deep dive assessment | TBD | 
Board approves Top Risks selected for initial deep dive work | TBD | 
Assign each of "Top Risks" to champion | TBD | 
Champion to create timeline for deep level assessment and recommendation plan | TBD | 
Update Board on deep level assessment and recommendations | TBD | 
Board approves recommendations | TBD | 
Monitor, Control & Communicate |  | 
Champion updates board on activities and key milestones | ongoing Board agenda | 
As initial "Top Risks" are mitigated, review current list of Risks and high level Assessment | ongoing Board agenda | 

## Slide 8: Next Steps:
Recanvas Directors to complete scoring for 3 additional items
Redistribute updated, prioritized list of Risks; highlight any “new” items that fall into “Critical” category
GM to determine how next steps in Timeline will be completed
Updates on Critical Item Mitigation work on future Board Agendas for progress update
Schedule session to debrief GM on other “non-risk specific insights” gained along the way

## Slide 9: Appendix
Risk Project Timeline
Risk Ranking Criteria and Prioritization Matrix
Risk Themes from Board Interviews
Risk Themes from Staff Interviews
Risk Themes from Past Board Member Interviews

## Slide 10: Risk Project Timeline – Page 1
Appendix 1 – page 1

## Slide 11: Risk Project Timeline – Page 2
Appendix 1 – page 2

## Slide 12: Approved Risk Ranking Criteria and Prioritization Matrix
Appendix 2

## Slide 13: Risk Themes from Board
Appendix 3

## Slide 14: Risk Themes from Staff
Appendix 4

## Slide 15: Risk Themes from Past Board Members
Appendix 5